## Program Timeline & Budget
Program Component | Component's Total Budget* (USD) |  | 2021 | [11 empty] | 2022
|  | Total Hours Required | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Project 1: Redesigning the layout of the streaming service | 520000 | 1600 | bar: 2021 Jan to 2022 Apr
Project 2: Create a more a robust database to house viewer data | 120000 | 1040 | bar: 2021 Mar to 2022 Mar
Develop protocols to understand viewer journeys better | 20000 | 240 | bar: 2021 Jan to 2021 Aug
Restructured IT department to better meet the needs of the new database and streaming redesign | 140000 | 480 | bar: 2022 Apr to 2022 Sep
Training for customer service staff on new database | 110600 | 144 | bar: 2022 Apr to 2022 Dec
Program Total Budget | 910600 | 3504
*Excludes Salaries

## Project 1 Status Report
Work Burndown
Date | Hours Remaining
0 | 1600
2021-01-31 | 1500
2021-02-28 | 1400
2021-03-21 | 1299
2021-04-30 | 1139
2021-05-31 | 979
2021-06-30 | 819
2021-07-31 | 709
2021-08-31 | 594
2021-09-30 | 489
Budget vs Actual Cost
Date | Actual Cost | Budget
2021-01-31 | 32500 | 32500
2021-02-28 | 34500 | 32500
2021-03-21 | 20000 | 32500
2021-04-30 | 45900 | 32500
2021-05-31 | 26700 | 32500
2021-06-30 | 34000 | 32500
2021-07-31 | 34568 | 32500
2021-08-31 | 34872 | 32500
2021-09-30 | 34900 | 32500
Work Completed
Date | Remaining Work
2021-01-31 | 95
2021-02-28 | 88
2021-03-21 | 81
2021-04-30 | 77
2021-05-31 | 75
2021-06-30 | 69
2021-07-31 | 67
2021-08-31 | 61
2021-09-30 | 58

## Project 2 Status Report
Work Burndown
Date | Hours Remaining
0 | 1040
2021-01-31 | 1040
2021-02-28 | 1040
2021-03-21 | 950
2021-04-30 | 870
2021-05-31 | 794
2021-06-30 | 729
2021-07-31 | 647
2021-08-31 | 581
2021-09-30 | 503
Budget vs Actual Cost
Date | Actual Cost | Budget
2021-01-31 | 0 | 0
2021-02-28 | 0 | 0
2021-03-21 | 5000 | 9230.7692
2021-04-30 | 6000 | 9230.7692
2021-05-31 | 6500 | 9230.7692
2021-06-30 | 8000 | 9230.7692
2021-07-31 | 4300 | 9230.7692
2021-08-31 | 5400 | 9230.7692
2021-09-30 | 5320 | 9230.7692
Work Completed
Date | Remaining Work
2021-01-31 | 0
2021-02-28 | 0
2021-03-21 | 97
2021-04-30 | 91
2021-05-31 | 88
2021-06-30 | 84
2021-07-31 | 77
2021-08-31 | 73
2021-09-30 | 70