## Program Timeline & Budget
Program Component | Component's Total Budget* (USD) |  | 2021 | [11 empty] | 2022
|  | Total Hours Required | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Project 1: Enterprise Resource Planning (ERP) Implementation | 340000 | 1800 | bar: 2021 Jan to 2022 Jun
Project 2: Customer relationship management (CRM) Implementation | 59000 | 1040 | bar: 2021 Mar to 2022 Mar
Relationship Building Procedure | 20000 | 180 | bar: 2022 Apr to 2022 Dec
Restructured finance department | 65000 | 480 | bar: 2022 Jul to 2022 Dec
ERP and CRM training procedure for managers | 110600 | 280 | bar: 2022 Apr to 2022 Oct
Program Total Budget | 594600 | 3780
*Excludes Salaries

## Project 1 Status Report
Work Burndown
Date | Hours Remaining
0 | 1800
2021-01-31 | 1700
2021-02-28 | 1600
2021-03-21 | 1499
2021-04-30 | 1339
2021-05-31 | 1179
2021-06-30 | 1019
2021-07-31 | 909
2021-08-31 | 794
2021-09-30 | 689
Budget vs Actual Cost
Date | Actual Cost | Budget
2021-01-31 | 18000 | 18888.8889
2021-02-28 | 19800 | 18888.8889
2021-03-21 | 20000 | 18888.8889
2021-04-30 | 18000 | 18888.8889
2021-05-31 | 18888 | 18888.8889
2021-06-30 | 20100 | 18888.8889
2021-07-31 | 19000 | 18888.8889
2021-08-31 | 17800 | 18888.8889
2021-09-30 | 18900 | 18888.8889
| 170488 | 170000
Work Completed
Date | Remaining Work
2021-01-31 | 95
2021-02-28 | 91
2021-03-21 | 88
2021-04-30 | 83
2021-05-31 | 81
2021-06-30 | 75
2021-07-31 | 73
2021-08-31 | 67
2021-09-30 | 64

## Project 2 Status Report
Work Burndown
Date | Hours Remaining
0 | 1040
2021-01-31 | 1040
2021-02-28 | 1040
2021-03-21 | 965
2021-04-30 | 885
2021-05-31 | 797
2021-06-30 | 732
2021-07-31 | 652
2021-08-31 | 572
2021-09-30 | 497
Budget vs Actual Cost
Date | Actual Cost | Budget
2021-01-31 | 0 | 0
2021-02-28 | 0 | 0
2021-03-21 | 5000 | 4538.4615
2021-04-30 | 6000 | 4538.4615
2021-05-31 | 6500 | 4538.4615
2021-06-30 | 8000 | 4538.4615
2021-07-31 | 4300 | 4538.4615
2021-08-31 | 5400 | 4538.4615
2021-09-30 | 5320 | 4538.4615
Work Completed
Date | Remaining Work
2021-01-31 | 0
2021-02-28 | 0
2021-03-21 | 94
2021-04-30 | 85
2021-05-31 | 77
2021-06-30 | 69
2021-07-31 | 64
2021-08-31 | 55
2021-09-30 | 47